## Backlog with Estimates and Cost
Name | Priority | Effort | Status | Description | Size | Estimate Effort | Actual Effort
Add Google Map | 4 |  | Complete | Add a Google Maps visual feature that shows the tested zone with using latitude and longitude coordinates. Basic screen capture of the location will be fine in order so client can see the exact location where the testing occurred. | Small | 3 | 4
Data paging separation | 11 |  |  | Put the heatmaps and google maps screen capture on separate pages. Have a title page that mentions Land Maverick, then the name of the golf course. The idea is that each golf course would have their own account, so title screens should be designated to the particular golf courses | Medium | 16 | 0
Add Login Screen | 12 |  |  | Make login screen. Assign a login to arbitrary golf club “Fairfield University Golf Club”. This way, the golf course can see just the data necessary on their golf course. Also make Admin login for myself so I can see the data of all golf courses. | Medium/Large | 24 | 0
Concurrent viewing of Google Map and Heatmap | 5 |  | Complete | Figure out a way to configure the google maps view and the heatmaps so possibly they could be viewed at the same time (this is not a necessity, just an idea). | Small | 2 | 2
Align Heatmap with headings on a single row | 6 |  | Complete |  | Small | 3 | 3
Deploy to AWS | 10 |  |  | Allow code to be running on AWS (can wait until next week for this) | Medium | 2 | 0
Scale Heatmaps based on amount of data gathered | 7 |  | Complete | When the data set explands and is larger than 5 by 5, scale the size of the squares in order to be sure the headings and heatmaps still align
Add code to Git Repository | 8 |  | Complete |  | Small | 4 | 4
Create Backlog | 1 |  | Complete |  | Small | 4 | 4
Heatmap integration into page | 2 |  | Complete |  | Medium | 16 | 16
Add Land Maverick Logo to Page | 3 |  | Complete |  | Small | 1 | 1
System Test of Phase 1 | 9 |  | Complete |  | Small | 8 | 6
Total | [6 empty] | 40 | 3000